Internal promotional campaign plan

People matter survey 2024

This document is part of the [People matter survey 2024 resources.](https://vpsc.vic.gov.au/data-collection/about-the-people-matter-survey/resources-for-survey-coordinators/survey-promotion-and-resources/)

## Template – Internal promotional campaign plan

Here are some tactics and you might consider for your campaign.

Adjust timelines as needed to suit your plan.

| When  | Tactic   | Activity  | Audience/stakeholder   |
| --- | --- | --- | --- |
| 23 September | Digital and offline | Use virtual background in all Teams meetingsUse signature banner in email communicationDisplay posters around the office | All staff |
| 25 September to 2 October | Digital | Send a promotional email from your head of organisationPublish a [news item](https://vpsc.vic.gov.au/wp-content/uploads/2024/06/People-matter-survey-2024-Sample-news-article-October.docx) on the intranetUse [speaking notes](https://vpsc.vic.gov.au/wp-content/uploads/2024/06/People-matter-survey-2024-Speaking-notes-October.docx) when speaking to staff | All staff |
| 7 to 11 October | Digital and offline | Send [invitation email](https://vpsc.vic.gov.au/wp-content/uploads/2024/06/People-matter-survey-2024-Invitation-and-reminder-emails-October.docx) to let employees know the survey has openedDisplay QR codes around the office |  All staff |
| 14- 18 October | Digital and offline | Provide participation rate via organisation’s newsletter/all staff | All staff |
| 25 October | Digital | Send [reminder email](https://vpsc.vic.gov.au/wp-content/uploads/2024/06/People-matter-survey-2024-Invitation-and-reminder-emails-October.docx) – survey closes | All staff |
| 28- 30 October [post survey] | Digital and offline | Provide final participation rate to EMB and all staff via newsletter | All staff |
| Late November | Digital | Survey results and benchmarking reports available on the online portal | All staff |
| End of table |  |   |   |